## Team Roster
Project Team Roster: MindScribe Publishing Platform
Role | Assigned To | Core Responsibilities
Front-end Developer | Majharul Islam Shajid | Blade/Inertia views, Tailwind styling, Editor.js integration, responsive & accessible UI.
Back-end Developer | Md Shomik Shahriar | Laravel app logic, Eloquent models, authentication, SQLite database, storage, deployments.
Scrum Master | Abir Hasan Arko | Facilitates ceremonies, maintains the Jira board, removes blockers, tracks velocity, reports to stakeholders.
Full-stack QA | Abir Hasan Arko | Test planning & execution across front-end and back-end, security/regression testing, defect tracking, release sign-off.

## Product Backlog
Project Backlog: MindScribe Publishing Platform
Project Name | MindScribe Web Application (Laravel & SQLite)
Client | Internal R&D / Open Source Community
Created By | Abir Hasan Arko (Scrum Master / Product Owner)
Creation Date | 2026-06-27
Approval Date | 2026-06-27
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
MS_1: User Authentication, secure session persistence, individual writer profiles, and app configuration panels. | MS-4 | User Registration and Sign Up | As a new user, I want to create an account using my name, email, and password, So that I can access personalized writing and reading features. | To Do | 1. System must use Laravel Breeze/Fortify for secure hashing. 2. Email must validate as unique in users table. 3. Enforce strong password complexity rule.
| MS-5 | User Login & Session Management | As a registered author or reader, I want to securely authenticate with my credentials, So that my workspace remains private and persistent. | To Do | 1. Session must persist via standard session cookies. 2. Failed login attempts must display clear errors and throttle after 5 counts.
| MS-11 | Author Profile Page View | As a visitor, I want to navigate to an author's profile page to see their picture, description, and list of stories, So that I can read more of their work. | To Do | 1. Must load all articles matching user_id. 2. Profiles page must render smoothly with minimal SQL query footprint via eager loading.
| MS-6 | My Profile Settings & Theme Toggle | As an authenticated user, I want to update my profile information and change between light and dark visual interfaces, So that the app suits my workspace environment. | To Do | 1. Theme state must persist inside the SQLite users table. 2. UI must apply standard dark variants instantly without flashing plain background on page refresh.
MS_2: Advanced Core Content Authoring Engine supporting multi-block formatting, file storage uploads, and classification metadata. | MS-8 | Article Editor Workspace Workspace (Draft Mode) | As an author, I want to create and auto-save new articles as drafts, So that my content is never lost mid-session. | To Do | 1. Status field can flag as 'draft' or 'published'. 2. Autosave interval script triggers every 30 seconds.
| MS-9 | Advanced Text Editor Block Engine | As an author, I want to format my content with structured paragraphs, headings, blockquotes, and link lists, So that my text layouts look crisp and professional. | To Do | 1. Implement using JavaScript interactive editor (TipTap/Editor.js). 2. Output format must clean-sanitize raw HTML chunks before execution.
| MS-10 | Media Uploads and Image Embeds | As an author, I want to add a high-resolution top banner image and embed dynamic inline figures inside article fields, So that my writing contains beautiful illustration elements. | To Do | 1. Images must save securely to local storage disks. 2. Only image URLs paths are saved inside SQLite database columns; no raw binary blobs.
| MS-12 | Genre Tag Mapping | As a publishing writer, I want to tag multiple specific genres on my article prior to hitting publish, So that my content registers under distinct catalog headings. | To Do | 1. System records relationships in standard article_genre pivot records. 2. Admin manageable list defaults.
MS_3: Content Discovery dashboards and interaction layer incorporating card layout design elements and feedback controls. | MS-7 | Photocard Grid Discovery Feed Dashboard | As a system reader, I want to view articles cataloged as clean visual postcards with title previews and large banner frames, So that browsing feels visually satisfying. | To Do | 1. Render cards using responsive CSS grid grids. 2. Pull excerpt tags cleanly to prevent container deformation.
| MS-13 | Dynamic Query Search & Genre Filtering | As a user, I want to input keyword terms or isolate topics by genre tag or author identity filter fields, So that I find specific stories instantly. | To Do | 1. Implement lightning fast local Eloquent query scopes. 2. Filtering actions can combine multiple criteria criteria simultaneously.
| MS-14 | Premium Typography Reader Layout | As an online reader, I want to view open articles wrapped in an elegant distraction-free reading typography view, So that I can easily digest long form publications. | To Do | 1. Utilize standardized Tailwind typography utility classes. 2. Enforce clean reading column margins.
| MS-15 | Interactive Article Comments Engine | As a platform member, I want to provide written responses under user posts, So that I can engage in discussions directly with authors. | To Do | 1. One-to-many relationship tracking against article logs. 2. Empty replies are disallowed via standard request rules.
| MS-16 | Star Metric Article Rating System | As a critical reviewer, I want to submit a 1 to 5 star evaluation value for open publications, So that I help surface highly scored write-ups. | To Do | 1. Restrict users to a single unique evaluation record per document. 2. Average rating updates dynamically on target dashboard layouts.

## Sprint Planning
Sprint Schedule & Scope Breakdown
Sprint | User Story ID | Feature/Title | Assigned To | Story Points | Start Date | End Date | Status | QA Owner
Sprint 1 | MS-4 | User Registration and Sign Up | Back-end Developer | 3 | 2026-07-01 | 2026-07-14 | Planned | Full-stack QA
Sprint 1 | MS-5 | User Login & Session Management | Back-end Developer | 2 | 2026-07-01 | 2026-07-14 | Planned | Full-stack QA
Sprint 1 | MS-6 | My Profile Settings & Theme Toggle | Front-end Developer | 3 | 2026-07-01 | 2026-07-14 | Planned | Full-stack QA
Sprint 1 | MS-7 | Photocard Grid Discovery Feed Dashboard | Front-end Developer | 5 | 2026-07-01 | 2026-07-14 | Planned | Full-stack QA
Sprint 2 | MS-8 | Article Editor Workspace Workspace (Draft Mode) | Front-end Developer | 5 | 2026-07-15 | 2026-07-28 | Planned | Full-stack QA
Sprint 2 | MS-9 | Advanced Text Editor Block Engine | Front-end Developer | 5 | 2026-07-15 | 2026-07-28 | Planned | Full-stack QA
Sprint 2 | MS-10 | Media Uploads and Image Embeds | Back-end Developer | 5 | 2026-07-15 | 2026-07-28 | Planned | Full-stack QA
Sprint 3 | MS-11 | Author Profile Page View | Front-end Developer | 3 | 2026-07-29 | 2026-08-11 | Planned | Full-stack QA
Sprint 3 | MS-12 | Genre Tag Mapping | Back-end Developer | 3 | 2026-07-29 | 2026-08-11 | Planned | Full-stack QA
Sprint 3 | MS-13 | Dynamic Query Search & Genre Filtering | Back-end Developer | 5 | 2026-07-29 | 2026-08-11 | Planned | Full-stack QA
Sprint 3 | MS-14 | Premium Typography Reader Layout | Front-end Developer | 3 | 2026-07-29 | 2026-08-11 | Planned | Full-stack QA
Sprint 4 | MS-15 | Interactive Article Comments Engine | Back-end Developer | 3 | 2026-08-12 | 2026-08-25 | Planned | Full-stack QA
Sprint 4 | MS-16 | Star Metric Article Rating System | Back-end Developer | 2 | 2026-08-12 | 2026-08-25 | Planned | Full-stack QA

## Tasks Matrix
Scrum Task Breakdown Standards
Front-end Developer Tasks | Back-end Developer Tasks | Full-stack QA Verification Tasks | Scrum Master Tasks
Inertia.js Layout Views & Blade Template Rendering Setup | Project Initialization & Requirement Analysis | Analysis of Feature Requirements | Sprint Planning & Backlog Grooming Facilitation
Tailwind Utility System Styles Definition (Light/Dark Switch Engine) | SQLite DB Engine Integration & Local WAL Tweaks | Formulation of Test Cases & Scenarios | Daily Stand-up Coordination & Jira Board Maintenance
Interactive Client JS Blocks Integration (Editor.js Layer) | Eloquent Model Declarations & Cascading Pivot Relational Rules | Writing Explicit Test Procedures | Sprint Review & Retrospective Facilitation
Photocard Grid Discovery Feed Dashboard UI Build | Authentication Control Routing (Laravel Breeze Implementation) | Executing Security Validation Sweeps | Impediment & Blocker Removal Tracking
Premium Typography Reader Layout Implementation | Asynchronous Media Upload Controllers & Storage Scripting | Executing Layout Matrix Multi-browser Audits | Velocity Tracking & Burndown Chart Monitoring
Profile Settings & Theme Toggle UI | Dynamic Local Scope Database Pipeline Query Search Building | Upload Payload Data Validation Scans | Stakeholder Communication & Status Reporting
Genre Tag Selector & Comments/Rating UI Components | Comprehensive Automated Back-end Integration & Unit Assertions | Testing Peripheral Visual State Caches | Cross-Team Dependency Coordination (Front-end / Back-end / QA)
Responsive Cross-Browser UI Polish & Accessibility Pass | Peer Pull Request Code-Review Audits | Boundary Input Stress Executions | Release Readiness & Sign-off Coordination
| Production System Virtual Server Deployments | Dynamic Query Parameter Functional Sweeps
Conducting Wide Regression Suite Executions
Defect Registry Tracking and Validation Cycles
Final Launch Staging Sign-off Confirmations